## OVERVIEW
[METAL-438] - Onboard & Certify a Mass Storage Server/Solution
Current Status: | In Review
Version | v2.0
Basic Info ¦ Project Documentation
Reference Information | Location
Main Issue [VIRT] | https://jiracloud.swg.usma.ibm.com:8443/browse/PMCLSC-90
JIRA Board
Slack | clsc_bm_onboard_certify_a_mass_storage_server_solution
AHA! | https://bigblue.aha.io/features/METAL-438
Confluence
Mural
Order form
Basic Info ¦ Project Team
OM
PM | Wael Ishack
Architects | Marl Price
Dev Managers
Dev Lead
Dev Team
QE Lead | Sunitha
QE Team | Deepak
QE Tasks
Dates | Start Date | End Date
Test Plan Creation | 2024-04-08
Test Plan Review and Updates
Test Plan Refinement
E2E Testing
History
Change Log | Date | Who made the changes
Started document
Completed the first draft
Test plan review
Test plan refinement
Test plan approval

## TEST_PLAN_DETAILS
Onboard & Certify a Mass Storage Server/Solution
Introduction
This document contains the main information to run the end to end testing to ensure Mass Storage Server/Solution is working fine
Objective
Ensure that Provision, OS reload and related BM operations works properly and error free for Mass Storage Server/Solution on IBM Cloud for Classic
Limitations
Debian does not support NVMe boot drives so that should not be in scope. Ubuntu is still in development and RHEL0 should be in scope. MSoft has not started development yet so that should be shown as unsupported at this time.
Scope
QA Team will test all functionality for Mass Storage Server/Solution on IBM Cloud for Classic.
TESTING SERVERS | OS | Storage Drive | Additional Requirements
6416H SPR processor |  | 36 drives | Validate the Intel Speed Functionality
|  |  | Verify 710 and E810 NICs will be supported | 710 = 10GHz and E810=25 GHz
|  |  | Verify TPM 2.0 works with this server | TPM in scope
| CentOS 9 |  | Verify SGX and AMX are supported with these processors | AMX out of scope
| Redhat 8.x-64 |  | Verify the Mirrored M.2 NVMe will work in this server | Primary
| Redhat 9.x-64 |  | Test with SATA HDD and SATA SSD and SSD SED | secondary
| Rocky Linux 8.x-64 |  | Verfy RAM densities for 64GB to 2TB
Rocky Linux 9.x-64
Ubuntu 22.04-64
Microsoft Windows 2019 FULL STD 64 bit 2019 FULL STD x64(Not supported at this time)
Microsoft Windows 2022 FULL STD 64 bit 2022 FULL STD x64(Not supported at this time)
VMware ESXi 7.0u3i
VMware ESXi 8.0u1
Strategy
The types of testing to be applied during the test execution of this project basically are the following:  Acceptance Test Once an environment has been set up for testing, automated and manual testing of functionality will be executed to validate expected outcomes.
Quality Engineering Team
Sunitha
Deepak
Testing Environment
The testing environmet is Staging / Production provided and configured by development team

## TC_MSS_6416H
Assignee | Summary | Test Plan | Verification | QE Assignee | Parent Id | Issue ID | Labels | Issue Type | Priority
sradharapu | TC_01_Provision : with 6416H SPR processor and CentOs9 | Verify that CentOS 9 Provisioning process can be completed without errors with below configuration * *SERVER*: SPR 6461H * *MOTHERBOARD*: ANY * *RAM*: 2048 GB * *OS*: CentOs 9 * *DRIVE*: 1 Nos. * *NETWORK INTERFACE*: Public and Private * *PORT SPEED*: 25 GHZ [~E810] * *DRIVE CONTROLLER*: Mirrorred M2 NVMe * *ADD-ON*: SGX | * Login to server and check for all the configurations are avaliable as expected * Validate Intel Speed Functionality | sradharapu | QEPVER-239 | QEPVER-244 | IQE-Project-Testing | Test Case | Major
dtogloor | TC_02_Provision : with 6416H SPR processor and Redhat 8.x-64 | Verify that Redhat 8.x-64 Provisioning process can be completed without errors with below configuration * *SERVER*: SPR 6461H * *MOTHERBOARD*: ANY * *RAM*: 512 GB * *OS*: Redhat 8.x-64 * *DRIVE*: 1 Nos. * *NETWORK INTERFACE*: Public and Private * *PORT SPEED*: 1 GHZ[~E710] * *DRIVE CONTROLLER*: Mirrorred M2 NVMe * *ADD-ON*: SGX | * Login to server and check for all the configurations are avaliable as expected * Validate Intel Speed Functionality | dtogloor | QEPVER-239 | QEPVER-244 | IQE-Project-Testing | Test Case | Major
sradharapu | TC_03_Provision : with 6416H SPR processor and Redhat 9.x-64 | Verify that Redhat 9.x-64 Provisioning process can be completed without errors with below configuration * *SERVER*: SPR 6461H * *MOTHERBOARD*: ANY * *RAM*: 1024 GB * *OS*: Redhat 9.x-64 * *DRIVE*: 1 Nos. * *NETWORK INTERFACE*: Public and Private * *PORT SPEED*: 25 GHz [~E810] * *DRIVE CONTROLLER*: Mirrorred M2 NVMe * *ADD-ON*: SGX | * Login to server and check for all the configurations are avaliable as expected * Validate Intel Speed Functionality | sradharapu | QEPVER-239 | QEPVER-244 | IQE-Project-Testing | Test Case | Major
dtogloor | TC_04_Provision : with 6416H SPR processor and Rocky Linux 8.x-64 | Verify that Rocky Linux 8.x-64 Provisioning process can be completed without errors with below configuration * *SERVER*: SPR 6461H * *MOTHERBOARD*: ANY * *RAM*: 256GB * *OS*: Rocky Linux 8.x-64 * *DRIVE*: 1 Nos. * *NETWORK INTERFACE*: Public and Private * *PORT SPEED*: 1 Ghz [~E710] * *DRIVE CONTROLLER*: Mirrorred M2 NVMe * *ADD-ON*: SGX | * Login to server and check for all the configurations are avaliable as expected * Validate Intel Speed Functionality | dtogloor | QEPVER-239 | QEPVER-244 | IQE-Project-Testing | Test Case | Major
sradharapu | TC_05_Provision : with 6416H SPR processor and Rocky Linux 9.x-64 | Verify that Rocky Linux 9.x-64 Provisioning process can be completed without errors with below configuration * *SERVER*: SPR 6461H * *MOTHERBOARD*: ANY * *RAM*: 2048 GB * *OS*: Rocky Linux 9.x-64 * *DRIVE*: 1 Nos. * *NETWORK INTERFACE*: Public and Private * *PORT SPEED*: 25 GHz [~E810] * *DRIVE CONTROLLER*: Mirrorred M2 NVMe * *ADD-ON*: SGX | * Login to server and check for all the configurations are avaliable as expected * Validate Intel Speed Functionality | sradharapu | QEPVER-239 | QEPVER-244 | IQE-Project-Testing | Test Case | Major
dtogloor | TC_06_Provision : with 6416H SPR processor and Ubuntu 22.04-64 | Verify that Ubuntu 22.04-64 Provisioning process can be completed without errors with below configuration * *SERVER*: SPR 6461H * *MOTHERBOARD*: ANY * *RAM*: 256 GB * *OS*: Ubuntu 22.04-64 * *DRIVE*: 36 Nos. * *NETWORK INTERFACE*: Public and Private * *PORT SPEED*: 1 Ghz [~E710] * *DRIVE CONTROLLER*: Mirrorred M2 NVMe * *ADD-ON*: SGX | * Login to server and check for all the configurations are avaliable as expected * Validate Intel Speed Functionality | dtogloor | QEPVER-239 | QEPVER-244 | IQE-Project-Testing | Test Case | Major
sradharapu | TC_07_Provision : with 6416H SPR processor and Ubuntu 22.04-64 | Verify that Ubuntu 22.04-64 Provisioning process can be completed without errors with below configuration * *SERVER*: SPR 6461H * *MOTHERBOARD*: ANY * *RAM*: 2048 GB * *OS*: Ubuntu 22.04-64 * *DRIVE*: 1 Nos. * *NETWORK INTERFACE*: Public and Private * *PORT SPEED*: 25 Ghz [~E810] * *DRIVE CONTROLLER*: Mirrorred M2 NVMe * *ADD-ON*: SGX | * Login to server and check for all the configurations are avaliable as expected * Validate Intel Speed Functionality | sradharapu | QEPVER-239 | QEPVER-244 | IQE-Project-Testing | Test Case | Major
dtogloor | TC_08_Provision : with 6416H SPR processor and Microsoft Windows 2019 FULL STD 64 bit 2019 FULL STD x64 | Verify that Microsoft Windows 2019 FULL STD 64 bit 2019 FULL STD x64 Provisioning process can be completed without errors with below configuration * *SERVER*: SPR 6461H * *MOTHERBOARD*: ANY * *RAM*: 2048 GB * *OS*: Microsoft Windows 2019 FULL STD 64 bit 2019 FULL STD x64 * *DRIVE*: 1 Nos. * *NETWORK INTERFACE*: Public and Private * *PORT SPEED*: 1 Ghz [~E710] * *DRIVE CONTROLLER*: Mirrorred M2 NVMe * *ADD-ON*: SGX | * Login to server and check for all the configurations are avaliable as expected * Validate Intel Speed Functionality | dtogloor | QEPVER-239 | QEPVER-244 | IQE-Project-Testing | Test Case | Major
sradharapu | TC_09_Provision : with 6416H SPR processor and Microsoft Windows 2022 FULL STD 64 bit 2022 FULL STD x64 | Verify that Microsoft Windows 2022 FULL STD 64 bit 2022 FULL STD x64 Provisioning process can be completed without errors with below configuration * *SERVER*: SPR 6461H * *MOTHERBOARD*: ANY * *RAM*: 256 GB * *OS*: Microsoft Windows 2022 FULL STD 64 bit 2022 FULL STD x64 * *DRIVE*: 1 Nos. * *NETWORK INTERFACE*: Public and Private * *PORT SPEED*: 25 Ghz [~E810] * *DRIVE CONTROLLER*: Mirrorred M2 NVMe * *ADD-ON*: SGX | * Login to server and check for all the configurations are avaliable as expected * Validate Intel Speed Functionality | sradharapu | QEPVER-239 | QEPVER-244 | IQE-Project-Testing | Test Case | Major
dtogloor | TC_10_Provision : with 6416H SPR processor and VMware ESXi 7.0u3i | Verify that VMware ESXi 7.0u3i Provisioning process can be completed without errors with below configuration * *SERVER*: SPR 6461H * *MOTHERBOARD*: ANY * *RAM*: 256 GB * *OS*: VMware ESXi 7.0u3i * *DRIVE*: 1 Nos. * *NETWORK INTERFACE*: Public and Private * *PORT SPEED*: 1 Ghz [~E710] * *DRIVE CONTROLLER*: Mirrorred M2 NVMe * *ADD-ON*: SGX | * Login to server and check for all the configurations are avaliable as expected * Validate Intel Speed Functionality | dtogloor | QEPVER-239 | QEPVER-244 | IQE-Project-Testing | Test Case | Major
sradharapu | TC_11_Provision : with 6416H SPR processor and VMware ESXi 7.0u3i | Verify that VMware ESXi 7.0u3i Provisioning process can be completed without errors with below configuration * *SERVER*: SPR 6461H * *MOTHERBOARD*: ANY * *RAM*: 256 GB * *OS*: VMware ESXi 7.0u3i * *DRIVE*: 1 Nos. * *NETWORK INTERFACE*: Public and Private * *PORT SPEED*: 1 Ghz [~E810] * *DRIVE CONTROLLER*: Mirrorred M2 NVMe * *ADD-ON*: SGX | * Login to server and check for all the configurations are avaliable as expected * Validate Intel Speed Functionality | sradharapu | QEPVER-239 | QEPVER-244 | IQE-Project-Testing | Test Case | Major
dtogloor | TC_12_Provision : with 6416H SPR processor and VMware ESXi 8.0u1 | Verify that VMware VMware ESXi 8.0u1 Provisioning process can be completed without errors with below configuration * *SERVER*: SPR 6461H * *MOTHERBOARD*: ANY * *RAM*: 2048 GB * *OS*: VMware ESXi 8.0u1 * *DRIVE*: 1 Nos. * *NETWORK INTERFACE*: Public and Private * *PORT SPEED*: 25 Ghz [~E710] * *DRIVE CONTROLLER*: Mirrorred M2 NVMe * *ADD-ON*: SGX | * Login to server and check for all the configurations are avaliable as expected * Validate Intel Speed Functionality | dtogloor | QEPVER-239 | QEPVER-244 | IQE-Project-Testing | Test Case | Major
sradharapu | TC_13_Provision : with 6416H SPR processor and VMware ESXi 8.0u1 | Verify that VMware VMware ESXi 8.0u1 Provisioning process can be completed without errors with below configuration * *SERVER*: SPR 6461H * *MOTHERBOARD*: ANY * *RAM*: 2048 GB * *OS*: VMware ESXi 8.0u1 * *DRIVE*: 1 Nos. * *NETWORK INTERFACE*: Public and Private * *PORT SPEED*: 25 Ghz [~E810] * *DRIVE CONTROLLER*: Mirrorred M2 NVMe * *ADD-ON*: SGX | * Login to server and check for all the configurations are avaliable as expected * Validate Intel Speed Functionality | sradharapu | QEPVER-239 | QEPVER-244 | IQE-Project-Testing | Test Case | Major
sradharapu | TC_14_Reload : TC-01 with CentOs 9 | *Verify that reload process for TC-01* * Previous OS: Centos 9 * Next OS : Centos 9 | * Login to server and check for all the configurations are avaliable as expected * Validate Intel Speed Functionality | sradharapu | QEPVER-239 | QEPVER-244 | IQE-Project-Testing | Test Case | Major
dtogloor | TC_15_Reload : TC-02 with Redhat 9 | *Verify that reload process for TC-02* * Previous OS: Redhat 8 * Next OS : Redhat 9 | * Login to server and check for all the configurations are avaliable as expected * Validate Intel Speed Functionality | dtogloor | QEPVER-239 | QEPVER-244 | IQE-Project-Testing | Test Case | Major
sradharapu | TC_16_Reload : TC-03 with Redhat 8 | *Verify that reload process for TC-03* * Previous OS: Redhat 9 * Next OS : Redhat 8 | * Login to server and check for all the configurations are avaliable as expected * Validate Intel Speed Functionality | sradharapu | QEPVER-239 | QEPVER-244 | IQE-Project-Testing | Test Case | Major
dtogloor | TC_17_Reload : TC-04 with Rocky Linux 9 | *Verify that reload process for TC-04* * Previous OS: Rocky linux 8 * Next OS : Redhat 9 | * Login to server and check for all the configurations are avaliable as expected * Validate Intel Speed Functionality | dtogloor | QEPVER-239 | QEPVER-244 | IQE-Project-Testing | Test Case | Major
sradharapu | TC_18_Reload : TC-05 with Rocky Linux 8 | *Verify that reload process for TC-05* * Previous OS: Rocky linux 9 * Next OS : Redhat 8 | * Login to server and check for all the configurations are avaliable as expected * Validate Intel Speed Functionality | sradharapu | QEPVER-239 | QEPVER-244 | IQE-Project-Testing | Test Case | Major
dtogloor | TC_19_Reload : TC-06 with Ubuntu 22.04-64 | *Verify that reload process for TC-06* * Previous OS: Ubuntu 22.04-64 * Next OS : Ubuntu 22.04-64 | * Login to server and check for all the configurations are avaliable as expected * Validate Intel Speed Functionality | dtogloor | QEPVER-239 | QEPVER-244 | IQE-Project-Testing | Test Case | Major
sradharapu | TC_20_Reload : TC-07 with Ubuntu 24.04-64 | *Verify that reload process for TC-07* * Previous OS: Ubuntu 22.04-64 * Next OS : Ubuntu 24.04-64 | * Login to server and check for all the configurations are avaliable as expected * Validate Intel Speed Functionality | sradharapu | QEPVER-239 | QEPVER-244 | IQE-Project-Testing | Test Case | Major
dtogloor | TC_21_Reload : TC-08 with Microsoft Windows 2022 FULL STD 64 bit 2019 FULL STD x64 | *Verify that reload process for TC-08* * Previous OS: Microsoft Windows 2022 FULL STD 64 bit 2019 FULL STD x64 * Next OS : Microsoft Windows 2022 FULL STD 64 bit 2019 FULL STD x64 | * Login to server and check for all the configurations are avaliable as expected * Validate Intel Speed Functionality | dtogloor | QEPVER-239 | QEPVER-244 | IQE-Project-Testing | Test Case | Major
sradharapu | TC_22_Reload : TC-09 with Microsoft Windows 2022 FULL STD 64 bit 2022 FULL STD x64 | *Verify that reload process for TC-09* * Previous OS: Microsoft Windows 2022 FULL STD 64 bit 2022 FULL STD x64 * Next OS : Microsoft Windows 2022 FULL STD 64 bit 2019 FULL STD x64 | * Login to server and check for all the configurations are avaliable as expected * Validate Intel Speed Functionality | sradharapu | QEPVER-239 | QEPVER-244 | IQE-Project-Testing | Test Case | Major
dtogloor | TC_23_Reload : TC-10 with Microsoft VMware ESXi 8.0u1 | *Verify that reload process for TC-10* * Previous OS: VMware ESXi 7.0u3i * Next OS : Microsoft VMware ESXi 8.0u1 | * Login to server and check for all the configurations are avaliable as expected * Validate Intel Speed Functionality | dtogloor | QEPVER-239 | QEPVER-244 | IQE-Project-Testing | Test Case | Major
sradharapu | TC_23_Reload : TC-11 with VMware ESXi 7.0u3i | *Verify that reload process for TC-11* * Previous OS: Microsoft VMware ESXi 8.0u1 * Next OS : VMware ESXi 7.0u3i | * Login to server and check for all the configurations are avaliable as expected * Validate Intel Speed Functionality | sradharapu | QEPVER-239 | QEPVER-244 | IQE-Project-Testing | Test Case | Major
sradharapu | TC_24_Reclaim : the server TC_14 | *Verify that the server is reclaimed sucessfully* | *Validate Reclaimed Successfully* | sradharapu | QEPVER-239 | QEPVER-244 | IQE-Project-Testing | Test Case | Major
dtogloor | TC_25_Reclaim : the server TC_15 | *Verify that the server is reclaimed sucessfully* | *Validate Reclaimed Successfully* | dtogloor | QEPVER-239 | QEPVER-244 | IQE-Project-Testing | Test Case | Major
sradharapu | TC_26_Reclaim : the server TC_15 | *Verify that the server is reclaimed sucessfully* | *Validate Reclaimed Successfully* | sradharapu | QEPVER-239 | QEPVER-244 | IQE-Project-Testing | Test Case | Major
dtogloor | TC_27_Reclaim : the server TC_16 | *Verify that the server is reclaimed sucessfully* | *Validate Reclaimed Successfully* | dtogloor | QEPVER-239 | QEPVER-244 | IQE-Project-Testing | Test Case | Major
sradharapu | TC_28_Reclaim : the server TC_17 | *Verify that the server is reclaimed sucessfully* | *Validate Reclaimed Successfully* | sradharapu | QEPVER-239 | QEPVER-244 | IQE-Project-Testing | Test Case | Major
dtogloor | TC_29_Reclaim : the server TC_18 | *Verify that the server is reclaimed sucessfully* | *Validate Reclaimed Successfully* | dtogloor | QEPVER-239 | QEPVER-244 | IQE-Project-Testing | Test Case | Major
sradharapu | TC_30_Reclaim : the server TC_19 | *Verify that the server is reclaimed sucessfully* | *Validate Reclaimed Successfully* | sradharapu | QEPVER-239 | QEPVER-244 | IQE-Project-Testing | Test Case | Major
dtogloor | TC_31_Reclaim : the server TC_20 | *Verify that the server is reclaimed sucessfully* | *Validate Reclaimed Successfully* | dtogloor | QEPVER-239 | QEPVER-244 | IQE-Project-Testing | Test Case | Major
sradharapu | TC_32_Reclaim : the server TC_21 | *Verify that the server is reclaimed sucessfully* | *Validate Reclaimed Successfully* | sradharapu | QEPVER-239 | QEPVER-244 | IQE-Project-Testing | Test Case | Major
dtogloor | TC_33_Reclaim : the server TC_22 | *Verify that the server is reclaimed sucessfully* | *Validate Reclaimed Successfully* | dtogloor | QEPVER-239 | QEPVER-244 | IQE-Project-Testing | Test Case | Major
sradharapu | TC_34_Reclaim : the server TC_23 | *Verify that the server is reclaimed sucessfully* | *Validate Reclaimed Successfully* | sradharapu | QEPVER-239 | QEPVER-244 | IQE-Project-Testing | Test Case | Major

## 6416H
Provision Test for Onboard & Certify a Mass Storage Server/Solution
sl.No# | Tester | Description | Validations | Priority | Status | Automated? | Blocked? | Comments
TC-01 |  | Verify that CentOS 9 Provisioning process can be completed without errors with below configuration SERVER: 6416H No. of drives: 1 RAM: 2048GB drive: Mirrorred M2 NVMe port speed: 25 GHZ [~E810] AddOn: SGX | Login to server and check for all the configurations are avaliable as expected Validate Intel Speed Functionality | Major
TC-02 |  | Verify that Redhat 8.x-64 Provisioning process can be completed without errors with below configuration SERVER: 6416H No. of drives:1 RAM: 512 GB drive: Mirrorred M2 NVMe port speed: 1 GHZ[~E710] AddOn: SGX | Login to server and check for all the configurations are avaliable as expected Validate Intel Speed Functionality | Major
TC-03 |  | Verify that Redhat 9.x-64 Provisioning process can be completed without errors with below configuration SERVER: 6416H No. of drives:1 RAM: 1024 GB drive: Mirrorred M2 NVMe port speed: 25 GHz [~E810] AddOn: SGX | Login to server and check for all the configurations are avaliable as expected Validate Intel Speed Functionality | Major
TC-04 |  | Verify that Rocky Linux 8.x-64 Provisioning process can be completed without errors with below configuration SERVER: 6416H No. of drives:1 RAM: 256GB drive: Mirrorred M2 NVMe port speed: 1 Ghz [~E710] AddOn: SGX | Login to server and check for all the configurations are avaliable as expected Validate Intel Speed Functionality | Major
TC-05 |  | Verify that Rocky Linux 9.x-64 Provisioning process can be completed without errors with below configuration SERVER: 6416H No. of drives:1 RAM: 2048 GB drive: Mirrorred M2 NVMe port speed: 25 Ghz [~E810] AddOn: SGX | Login to server and check for all the configurations are avaliable as expected Validate Intel Speed Functionality | Major
TC-06 |  | Verify that Ubuntu 22.04-64 Provisioning process can be completed without errors with below configuration SERVER: 6416H No. of drives: 36 RAM: 256 GB drive: Mirrorred M2 NVMe port speed: 1 Ghz [~E710] AddOn: SGX | Login to server and check for all the configurations are avaliable as expected Validate Intel Speed Functionality | Major
TC-07 |  | Verify that Ubuntu 22.04-64 Provisioning process can be completed without errors with below configuration SERVER: 6416H No. of drives:1 RAM: 2048 GB drive: Mirrorred M2 NVMe port speed: 25 Ghz [~E810] AddOn: SGX | Login to server and check for all the configurations are avaliable as expected Validate Intel Speed Functionality | Major
TC-08 |  | Verify that Microsoft Windows 2019 FULL STD 64 bit 2019 FULL STD x64 Provisioning process can be completed without errors with below configuration SERVER: 6416H No. of drives:1 RAM: 2048 GB drive: Mirrorred M2 NVMe port speed: 1 Ghz [~E710] AddOn: SGX | Login to server and check for all the configurations are avaliable as expected Validate Intel Speed Functionality | Major |  |  |  | Thom BAKER 18:05 @Sunitha Debian does not support NVMe boot drives so that should not be in scope. Ubuntu is still in development and RHEL0 should be in scope. MSoft has not started development yet so that should be shown as unsupported at this time.
TC-09 |  | Verify that Microsoft Windows 2022 FULL STD 64 bit 2022 FULL STD x64 Provisioning process can be completed without errors with below configuration SERVER: 6416H No. of drives:1 RAM: 256 GB drive: Mirrorred M2 NVMe port speed: 25 Ghz [~E810] AddOn: SGX | Login to server and check for all the configurations are avaliable as expected Validate Intel Speed Functionality | Major |  |  |  | Thom BAKER 18:05 @Sunitha Debian does not support NVMe boot drives so that should not be in scope. Ubuntu is still in development and RHEL0 should be in scope. MSoft has not started development yet so that should be shown as unsupported at this time.
TC-10 |  | Verify that VMware ESXi 7.0u3i Provisioning process can be completed without errors with below configuration SERVER: 6416H No. of drives:1 RAM: 256 GB drive: Mirrorred M2 NVMe port speed: 1 Ghz [~E710] AddOn: SGX | Login to server and check for all the configurations are avaliable as expected Validate Intel Speed Functionality | Major
TC-11 |  | Verify that VMware ESXi 7.0u3i Provisioning process can be completed without errors with below configuration SERVER: 6416H No. of drives:1 RAM: 256 GB drive: Mirrorred M2 NVMe port speed: 1 Ghz [~E810] AddOn: SGX
TC-12 |  | Verify that VMware ESXi 8.0u1 Provisioning process can be completed without errors with below configuration SERVER: 6416H No. of drives:1 RAM: 2048 GB drive: Mirrorred M2 NVMe port speed: 25 Ghz [~E710] AddOn: SGX
TC-13 |  | Verify that VMware ESXi 8.0u1 Provisioning process can be completed without errors with below configuration SERVER: 6416H No. of drives:1 RAM: 2048 GB drive: Mirrorred M2 NVMe port speed: 25 Ghz [~E810] AddOn: SGX | Login to server and check for all the configurations are avaliable as expected Validate Intel Speed Functionality | Major
Reload Test for Onboard & Certify a Mass Storage Server/Solution
sl.No# | Tester | Description | Validations | Priority | Status | Automated? | Blocked? | Comments
TC-14 |  | Verify that reload process for TC-03 previous OS: Centos 9 next OS : centos 9 | Login to server and check for all the configurations are avaliable as expected Validate Intel Speed Functionality | Major
TC-15 |  | Verify that reload process for TC-05 previous OS: Redhat 8 next OS : Redhat 9 | Login to server and check for all the configurations are avaliable as expected Validate Intel Speed Functionality | Major
TC-16 |  | Verify reload process for TC-06 previous os: Redhat 9 next os: Redhat 8 | Login to server and check for all the configurations are avaliable as expected Validate Intel Speed Functionality | Major
TC-17 |  | Verify reload process for TC-07 previous os: Rocky linux 8 next os: Rocky Linux 9 | Login to server and check for all the configurations are avaliable as expected Validate Intel Speed Functionality | Major
TC-18 |  | Verify reload process for TC-08 previous os: Rocky linux 9 next os: Rocky Linux 8 | Login to server and check for all the configurations are avaliable as expected Validate Intel Speed Functionality | Major
TC-19 |  | Verify reload process for TC-10 to same os | Login to server and check for all the configurations are avaliable as expected Validate Intel Speed Functionality | Major
TC-20 |  | Verify that reload process can be completed for TC-11 previous OS:Microsoft Windows 2019 FULL STD 64 bit 2019 FULL STD x64 next Os:Microsoft Windows 2022 FULL STD 64 bit 2019 FULL STD x64 | Login to server and check for all the configurations are avaliable as expected Validate Intel Speed Functionality | Major |  |  |  | Thom BAKER 18:05 @Sunitha Debian does not support NVMe boot drives so that should not be in scope. Ubuntu is still in development and RHEL0 should be in scope. MSoft has not started development yet so that should be shown as unsupported at this time.
TC-21 |  | Verify that reload process can be completed for TC-12 previous OS: Microsoft Windows 2022 FULL STD 64 bit 2019 FULL STD x64 next Os: Microsoft Windows 2019 FULL STD 64 bit 2019 FULL STD x64 | Login to server and check for all the configurations are avaliable as expected Validate Intel Speed Functionality | Major |  |  |  | Thom BAKER 18:05 @Sunitha Debian does not support NVMe boot drives so that should not be in scope. Ubuntu is still in development and RHEL0 should be in scope. MSoft has not started development yet so that should be shown as unsupported at this time.
TC-22 |  | Verify that reload process can be completed for TC-13 previous OS:VMware ESXi 7.0u3i next Os:Microsoft VMware ESXi 8.0u1 | Login to server and check for all the configurations are avaliable as expected Validate Intel Speed Functionality | Major
TC-23 |  | Verify that reload process can be completed for TC-14 previous OS:VMware ESXi 8.0u1 next Os:Microsoft VMware ESXi 7.0u3i | Login to server and check for all the configurations are avaliable as expected Validate Intel Speed Functionality | Major
Reclaim Test for Onboard & Certify a Mass Storage Server/Solution
sl.No# | Tester | Description | Validations | Priority | Status | Automated? | Blocked? | Comments
TC-24 | sradharapu | Verify that it is possible to reclaim TC-18 |  | Major
TC-25 |  | Verify that it is possible to reclaim TC-20 |  | Major
TC-26 |  | Verify that it is possible to reclaim TC-21 |  | Major
TC-27 |  | Verify that it is possible to reclaim TC-22 |  | Major
TC-28 |  | Verify that it is possible to reclaim TC-23 |  | Major
TC-29 |  | Verify that it is possible to reclaim TC-25 |  | Major
TC-30 |  | Verify that it is possible to reclaim TC-28 |  | Major
TC-31 |  | Verify that it is possible to reclaim TC-29 |  | Major

## UI_TESTING
UI Form: BM
# | Tester | Description | Validations | Priority | Status | Automated? | Blocked? | Comments

## Issue Found
How to validate intel speed functionality